## Master
USER STORY #2: | Number | Task | Subtasks | Hours?
| 1 | Create splash/banner or login page |  | 6
| 2 | User logs in
|  |  | Set up account | 10
|  |  | 3rd party authentication login | 5
| 3 | Search Bar
|  |  | Foods | 8
|  |  | Radius through google maps | 6
| 4 | Using databases for search bar searches |  | 10
| 5 | Counter for # of people who went to x restaurant | Counting individual users on platform | 5
|  |  | Reviews through yelp and tripadvisor | 5
| 6 | Creating Interface | Visuals | 10
|  |  | Profile | 10
|  |  | Search bar + Search options | 10
|  |  | History | 5
|  |  | Favorites | 5
|  |  | Recommended? | 20
|  |  | Deals | 20
| 7 | Have option of using multiple keywords/filters for search | Yummly approach? | 10
| 8 | Change style to search for ingredients instead of restaurants
| 9 | Using same process, searches for ingredients using same settings/filters
| 10 | Distance | Location Identifier | 5
|  |  | ETA for each transportation | 5
|  |  | Distance from restaurants | 5
|  |  | Distance from places w/ingredients | 5
| 11 | Layout for list of restaurants / recipes |  | 10
|  |  |  | 154 | Total

## Danny
ESTIMATED TIME (In Hours) | TASKS
6 | Logging through social media (gmail, facebook, instagram, etc)
24 | Estimated time of arrival to x place based off of certain transportation systems
6 | Easily accessible and clear search bar
6 | Location identifier
24 | Distance searching
2 | Counter for number of people ordering x food
6 | Food options with it said ingredients
6 | Ratings of restaurants
6 | Restaurants with said foods
6 | Signing up through making an account
6 | Recipes for desired food
30 | Layout (tabs for profile, search bar, recipes, restaurants, history, favorites tab, recommended, deals, preferences)
6 | Locations with ingredients for food
20 | Visuals
4 | Saving previous selected options / searches
2 | Ratings of food / or & restaurants

## Michael
1. To log in, the user must sign in using google.
Write an interface asking the user to sign in or make an account. | 5
Authenticate through google. | 2
2. Fills in search bar with ingredients and set radius.
Make a display with the search bar. | 10
Incorporate data for the ingredients. | 2
Use database to pick out dish. | 2
Use google maps for radius search. | 2
Use yelp to see restaurants in area. | 2
3. No restaurant options, decide to make food.
Use database to find market with ingredients. | 2
Use google maps to find closest market. | 2
Save choice in profile. | 2
| 31 | Total hours

## Ryan
Number | Tasks | Hours?
1 | User needs to set up account | 5
2 | User needs to consider 3rd party authentication login | 2
3 | Need to make sure user is already logged in | 4
4 | Need to implement some sort of search query in database (types in meat) | 5
5 | Search filter contains ingredients/keywords | 7
6 | User will add more keywords to specify search | 2
7 | Using keyword search, user finds restaurants based on proximity | 4
8 | If user cannot find something that they like, they can change search filters/options | 4
9 | Instead of looking for places to eat, they can instead choose to make the dish itself | 2
10 | Using similar tools, search of markets are based on ingredient and proximity | 10

## Mia
| Tasks | Hours
1 | Create splash/banner or login page | 5
2 | User logs in | 15
3 | Search Bar | 15
4 | Using databases for search bar searches | 12
5 | Counter for # of people who went to x restaurant | 25
6 | Creating Interface | 85
7 | Have option of using multiple keywords/filters for search | 10
8 | Change style to search for ingredients instead of restaurants | 10
9 | Using same process, searches for ingredients using same settings/filters | 10
10 | Distance | 25
11 | Layout for list of restaurants / recipes | 8

## Jaeger
| Tasks | Estimated Hours
1 | The user needs to sign into their account on the homepage. | 5
2 | Verification of the account and link to previous searches | 5
3 | Efficient search bar thats able to look for ingredients | 4
4 | Use a databse to find approrpiate options | 15
5 | Implement a search filter | 6
6 | Seperate database that gives the options based on location | 13
7 | Create a page that offers options that match the search, and possible other recommendations | 20
8 | Possibility of no matches, link to recommendations or nearest match | 4
9 | Easy switch back to remove the location filter | 4
10 | Search filter for markets with the appropriate ingredients | 7
11 | Save the receipe the user chooses, and create a clear page for the instructions | 8
12 | Save information to the user account | 2
13 | Convienent re search | 2
Total: 95